## Overview
Cross-Platform BI Migration Assistant
Power BI (.pbix) -> Tableau (.twb) ¦ build tracker
Status | Build complete - 141 tests pass; both generated workbooks open in Tableau Desktop 2026.2; web UI + run_app.bat
Phase 1 | Retail Analysis: extract -> analyse -> convert. 16/16 data visuals migratable; 14 sheets, 3 dashboards
Phase 2 | Regional Sales stress test: 937 containers -> 55 data visuals; 47 sheets, 9 dashboards
Phase 3 | Model layer: 15 measures with full DAX read from Desktop's engine; 4 translated, 11 refused with reasons
Run | python -m src.cli "input/Retail Analysis Sample PBIX.pbix"
Extra files needed | None - .pbix alone is sufficient (D1)
Milestone progress
Done
In Progress
Not Started
Blocked
Total
% complete
How to use this workbook
Milestones - the build plan with a Verification column; Status is a dropdown that rolls up here.
Architecture - which component owns what, and what it deliberately does NOT own.
Verified Findings - every format fact, tagged VERIFIED / DOCUMENTED / ASSUMPTION, with evidence.
Environment - machine facts: versions, paths, file hashes.
Decisions - what we chose, why, and what we rejected.
Risks & Questions - resolved items kept for the record; open items are future work.

## Milestones
Build Milestones - Power BI to Tableau Migration Assistant
ID | Phase | Step | Description | Component | Depends on | Status | Verification (how we proved it works) | Notes
M0 | Phase 0 - Investigation | Format discovery | Prove what .pbix contains; no invented behaviour. | Parser (research) | - | Done | 15 assumption tests pass; first run caught 2 wrong assumptions
M0.1 | Phase 0 - Investigation | Environment survey | Power BI Desktop, Tableau Desktop, live AS instance, Superstore reference. | - | M0 | Done | Versions, ports, paths on Environment sheet
M1 | Phase 1 - Retail Analysis | Extract: PbixReader | Open .pbix zip, decode Report/Layout (UTF-16LE), expose parts tolerantly. | Parser | M0 | Done | 11 tests: both files & vintages, error paths | src/parsers/pbix_reader.py
M2 | Phase 1 - Retail Analysis | Extract: Canonical model (IR) | Vendor-neutral Report / Page / Visual / FieldRef / Filter / DataModel. | Canonical model | M1 | Done | 6 tests incl. no-vendor-vocabulary guard | src/models/ir.py
M3 | Phase 1 - Retail Analysis | Extract: Layout -> IR | Nested JSON-in-string, projections + SemanticQuery + filters -> IR. | Parser | M2 | Done | 24 tests: Retail 24/16; Regional 937/55/45; all predicates mapped | src/parsers/layout_parser.py
M4 | Phase 1 - Retail Analysis | Analyse: Compatibility analyzer | Verdict + reason per visual; Markdown assessment. | Compatibility analyzer | M3 | Done | 7 tests: Retail 16/16 migratable; Regional 6 unsupported named | src/analyzers/compatibility.py
M5 | Phase 1 - Retail Analysis | Convert: Tableau generator | Emit .twb + header-only CSV following Superstore.twb. | Tableau generator | M4 | Done | 11 tests AND both workbooks OPEN in Tableau Desktop 2026.2 (load rk=ok) | src/generators/twb_writer.py
M6 | Phase 1 - Retail Analysis | CLI end-to-end | One command: .pbix -> assessment.md + summary.json + .twb + csv. | CLI | M5 | Done | 4 tests; python -m src.cli input/... runs clean | src/cli.py
M7 | Phase 2 - Second file | Stress test: Regional Sales | 937 containers, 22 visual types, subqueries in From. | All | M6 | Done | 47 sheets / 9 dashboards; opens in Tableau; nothing dropped silently | found the subquery-alias bug
M8 | Phase 3 - Model layer | Live model extraction (opt-in) | TMSCHEMA DMVs via the ADOMD client shipped in Desktop. | Parser | M7 | Done | 6 tests on real captured DMV JSON: 15 measures w/ DAX, 8 relationships | src/parsers/model_reader.py
M9 | Phase 3 - Model layer | DAX translator (named subset) | Arithmetic, comparisons, aggregates, DIVIDE/IF/BLANK; refuse the rest. | DAX translator | M8 | Done | 18 tests; Regional: 4 translated / 11 refused with reason | src/translators/dax_to_tableau.py
M10 | Phase 4 - Documentation | Two-audience codebase guide | Plain-English + technical explanation of every file. | - | M9 | Done | CODEBASE_GUIDE.xlsx + docs/CODEBASE_GUIDE.md generated from one source
M11 | Phase 5 - Product | Web UI + one-click launcher | FastAPI app over the shared pipeline; iOS-style UI with 4 themes, light/dark, animated backgrounds; run_app.bat bootstraps venv + libraries. | Web / launcher | M10 | Done | 15 web tests; UI driven end-to-end in the browser; run_app.bat verified from a clean copy with no venv | src/web, src/pipeline.py, run_app.bat
Rule: a milestone is Done only when its Verification column has actually been run and passed.

## Architecture
Architecture - component responsibilities
Layer | Component | Owns (role) | Responsibility | Explicitly does NOT own | File | Status
1. Input | PbixReader | Parser | Open the .pbix zip; decode Report/Layout as UTF-16LE JSON; expose parts tolerantly. | Any judgement about Tableau | src/parsers/pbix_reader.py | Done
1. Input | LayoutParser | Parser | Decode JSON-in-string fields; position from config.layouts[0].position; SemanticQuery Select/From -> fields; filters -> Condition trees. | Deciding whether a visual can be migrated | src/parsers/layout_parser.py | Done
1. Input | ModelReader (opt-in) | Parser | Measures / columns / relationships from Power BI Desktop's live AS instance via TMSCHEMA DMVs. | Running when Desktop is closed - degrades gracefully | src/parsers/model_reader.py | Done
2. Core | Intermediate Representation | Canonical model | Vendor-neutral Report / Page / Visual / FieldRef / Measure / Relationship. THE POINT OF THE PROJECT. | Either vendor's vocabulary | src/models/ir.py | Done
3. Analysis | Compatibility analyzer | Compatibility analyzer | IR + capability matrix -> direct / approximate / manual / unsupported / decorative, with reasons; writes assessment.md. | Writing any workbook | src/analyzers/compatibility.py | Done
3. Analysis | DAX translator | DAX translator | Named DAX subset -> Tableau calc text; raises UnsupportedDax otherwise. | Guessing; partial translation | src/translators/dax_to_tableau.py | Done
4. Output | Tableau generator | Tableau generator | IR -> .twb XML + header-only CSV; structure from Superstore.twb plus the loader requirements found by bisect. | Deciding what is migratable | src/generators/twb_writer.py | Done
5. Shell | CLI | CLI | Pipeline wiring; --model live / --model-dir; exit codes 0/1/2. | Any business logic | src/cli.py | Done

## Verified Findings
Findings - what we proved, what Microsoft documents, and what we assume
ID | Confidence | Area | Finding | Evidence
F1 | VERIFIED | Container | .pbix is a ZIP/OPC container. | zipfile.is_zipfile() true for both files
F2 | VERIFIED | Report | Report/Layout is UTF-16LE JSON with NO BOM; UTF-8 decoding fails. | First bytes 7b 00 22 00
F3 | VERIFIED | Report | config / query / filters / dataTransforms are JSON stored AS STRINGS (second json.loads). | isinstance(vc['config'], str)
F4 | VERIFIED | Report | Position is canonically config.layouts[0].position; top-level x/y is an optional rounded mirror. | Original Retail had none; re-saved Retail and Regional have both
F5 | VERIFIED | Report | 'query' and 'projections' do not imply each other (7 bound visuals without query; 3 textboxes with query). | Regional Sales census
F6 | VERIFIED | Report | Signal vs noise: Regional 937 containers, 55 data-bound; Retail 24 -> 16. | Full inventory walk
F7 | VERIFIED | Report | SemanticQueryDataShapeCommand distinguishes Column / Measure / Aggregation(Function int). | Both files; Function 0/1/3 cross-checked with Name prefixes
F8 | VERIFIED | Report | From entries can be SUBQUERIES ({Name, Expression:{Subquery}}) - alias resolves to inner entity. | Regional; crashed the first parser draft
F9 | VERIFIED | Report | Filter predicates seen: In, Comparison(kind 0-3), And, Not; literals 'x', 12L, 0.5M, true/false, null. | Census across both files
F10 | VERIFIED | Model | DataModel is an AS ABF backup, 30% printable; DAX not safely scrapeable from the file. | STREAM_STORAGE_SIGNATURE_ header; byte searches
F11 | VERIFIED | Model | The FULL model is readable from Desktop's live AS instance via TMSCHEMA DMVs (complete DAX, relationships, M). | localhost:52961 via AdomdClient shipped in Desktop bin
F12 | VERIFIED | Model | That route needs Desktop OPEN with the file; the port changes every launch. | msmdsrv PID present, then absent
F13 | DOCUMENTED | PBIP | PBIX <-> PBIP conversion only via Desktop File > Save as; cannot be automated. | MS Learn projects-overview FAQ (2026-08-18)
F14 | DOCUMENTED | PBIP | PBIP and PBIR are preview features with separate checkboxes; PBIR will become the only report format at GA. | MS Learn projects-report
F15 | VERIFIED | Tableau | Superstore.twbx ships with Tableau 2026.2 - the authoritative .twb reference. | C:\Program Files\Tableau\Tableau 2026.2\help\Workbooks\en_US
F16 | VERIFIED | Tableau | Tableau REQUIRES: document-format-change-manifest + source-build; explain-data node; simple-id on every sheet/dashboard/window; <style/> per table; >=1 worksheet. | ~60-variant bisect against Superstore.twb (findings section 7)
F17 | VERIFIED | Tableau | Tableau's loader is not a plain XML parser: empty shelves must be <rows></rows> not <rows />, and text-node newlines must be &#10; entities. | c3 vs card; s5 vs m8
F18 | VERIFIED | Tableau | Hand-written dashboard windows always fail; omit them and Tableau recreates them. | d1 opens, d4 fails
F19 | VERIFIED | Tableau | Optional: repository-location, mapsources, datasource-relationships, thumbnails, actions, metadata-records, fcp relation wrappers. | f-series and q-series
F20 | VERIFIED | Tableau | 'OPENED: Tableau - Book1/Book2' is a FALSE POSITIVE (silent failure + blank book). Pass = title equals file name and load rk=ok. | e2/e4/y1 re-runs
F21 | VERIFIED | Tooling | Windows console is cp1252; all IO must set encoding='utf-8'. | UnicodeEncodeError while probing
F23 | VERIFIED | Snapshots | Power BI's engine evaluates per-visual SUMMARIZECOLUMNS queries over ADOMD; headers come back as Table[Column] / [alias]. | Regional open in Desktop: 4,968 rows
F24 | VERIFIED | Report | Hierarchy levels are stored as HierarchyLevel expressions; name-only fields can be measures (Revenue Won) and must be re-classified from the model. | Rejected queries before the fix
F25 | VERIFIED | Sample data | Regional's RELATIVE MONTH ranges -92..-45 today (data ends 2022): its 'last 6 months' page filter empties 29 visuals in Power BI itself. | EVALUATE MIN/MAX against the live model
F22 | VERIFIED | Input | Retail Analysis was re-saved by Desktop 2.149 on 2026-09-12 (13.6MB -> 9.7MB, DataMashup gone, top-level x/y added); visuals unchanged. | SHA-256 changed; tests updated to hold across both vintages

## Environment
Environment - verified machine facts
Item | Value | Notes
Project root | C:\Redesign\BI_report_migration | Working directory
Source file 1 | Retail Analysis Sample PBIX.pbix | 9,71 MB (re-saved 2026-09-12) - 4 pages, 24 containers, 16 data-bound. PHASE 1 TARGET
Source file 1 SHA-256 | 3F03073ED49A9BA3A0CE81B2D8C42C390B01C95821C3DB0D8339A80C2D24EE91 | Original (13,6 MB) was 0D1B2ED3...; see F22
Source file 2 | Regional Sales Sample.pbix | 1,09 MB - 11 pages, 937 containers, 55 data-bound. PHASE 2 STRESS TEST
Source file 2 SHA-256 | ABA504345740406FE35EA83C4DC194BB408CE467F09840BAC1B82E5E8725CDAB | Unchanged
Python | 3.13.14 | Standard library at runtime; pytest 9.1.1 + openpyxl in .venv
Tests | 141 passing | python -m pytest
Launch | run_app.bat -> http://127.0.0.1:8765 | Creates .venv + installs libraries on first run
Power BI Desktop | 2.149.1252.0 (25.11) | C:\Program Files\Microsoft Power BI Desktop - MSI install
Tableau Desktop | 2026.2 (26.2.1782) | Both generated workbooks verified to open (load rk=ok)
Tableau reference workbook | Superstore.twbx | C:\Program Files\Tableau\Tableau 2026.2\help\Workbooks\en_US
AS client library | Microsoft.PowerBI.AdomdClient.dll | Ships in Power BI Desktop\bin; namespace Microsoft.AnalysisServices.AdomdClient
Live model port | read from AnalysisServicesWorkspaces\*\Data\msmdsrv.port.txt (UTF-16LE) | Changes every launch; discovered automatically by --model live
Outputs | output\<report>\ assessment.md, summary.json, measures.json, <report>.twb, data\model_stub.csv | Regenerate with python -m src.cli

## Decisions
Decision log - what we chose and why
ID | Date | Decision | Rationale | Alternative rejected
D1 | 2026-09-12 | Work from .pbix only; no PBIP/TMDL export required. | Report layer from Report/Layout; model layer from Desktop's live AS instance. Microsoft confirms PBIX->PBIP cannot be automated. | Manual PBIP export per file
D2 | 2026-09-12 | Never scrape DAX from the DataModel ABF blob. | Compressed; readable runs are fragments; would emit corrupted calculations. | Regex-harvesting literals
D3 | 2026-09-12 | Retail Analysis first; Regional Sales as stress test. | 24 vs 937 containers. | Starting with Regional
D4 | 2026-09-12 | Analyzer before generator. | Assessment is useful even for visuals we cannot emit. | Generator-first
D5 | 2026-09-12 | Translate only a NAMED DAX subset; refuse loudly otherwise. | Half-translating produces confidently wrong output (rule 8). | Best-effort translator
D6 | 2026-09-12 | Validate .twb against Superstore.twb, then open in Tableau Desktop. | Never invent the target format (rule 5). | Writing .twb from docs alone
D7 | 2026-09-12 | One flattened, header-only CSV datasource per workbook. | Data is locked in the model; shelves are preserved; user swaps in a real extract. | One datasource per table (needs blending), or a live extract
D8 | 2026-09-12 | Pies emitted as bars and downgraded to approximate. | Superstore has no pie worksheet to verify the angle encoding. | Guessing a <wedge-size> encoding
D9 | 2026-09-12 | Model extraction is opt-in (--model live / --model-dir). | Needs Desktop open; the tool must degrade gracefully. | Hard dependency on Desktop
D10 | 2026-09-12 | Do not emit dashboard windows. | Every hand-written form fails to load; Tableau recreates them (F18). | Copying Superstore's window shape
D11 | 2026-09-12 | Verify Tableau loading via its own log instead of the screen. | Screen control was declined; log.txt carries show-detailed-error-dialog and load-workbook rk=ok. | Asking the user to open each variant by hand
D12 | 2026-09-15 | Web app is a thin layer over one shared pipeline function. | CLI and UI call src.pipeline.run_pipeline; the server only validates paths and maps errors to HTTP codes, so they cannot disagree. | Duplicating orchestration in the server
D13 | 2026-09-15 | run_app.bat creates .venv and installs libraries automatically, keyed on a hash of requirements.txt. | Collaborators have Python only; second launches must be instant. | Asking users to pip install by hand
D14 | 2026-09-15 | Vanilla HTML/CSS/JS front-end, no build step. | Nothing to install beyond Python; the .bat stays simple; the UI ships inside the repo. | React/Vite toolchain
D15 | 2026-09-15 | Data snapshots are per visual: each visual's own SUMMARIZECOLUMNS, one datasource each. | Exact numbers including non-additive measures, no join logic, no translation risk; visuals without a snapshot keep the stub. | One flattened fact table (wrong totals for ratios/averages)
D16 | 2026-09-15 | Snapshots apply Power BI's filters by default; 'visual' and 'none' are explicit options. | Faithfulness first: a visual that is empty in Power BI stays empty and is explained; demos can opt out. | Silently dropping filters to make charts look full

## Risks & Questions
Risks and open questions
ID | Type | Item | Impact | Mitigation / outcome | Status
R1 | Resolved | Live model extraction in scope? | - | Implemented opt-in (D9); tested on captured fixtures; live path needs Desktop open. | Resolved
R2 | Resolved | Filter structures uncharacterised. | - | Characterised (F9) and parsed into the IR; listed in the assessment. | Resolved
R3 | Resolved | .twb generation harder than estimated. | It was: ~60 bisect runs. | All loader requirements found and encoded in the generator + tests (F16-F18). | Resolved
R4 | Risk | Report/Layout (PBIR-Legacy) is on a deprecation path. | High later | Parser interface allows a PBIR reader; not yet written. | Open - future work
R5 | Accepted | No Tableau equivalent for keyDrivers / decompositionTree / Q&A / custom visuals. | Low | Reported as unsupported with reasons; never dropped silently. | Accepted
R6 | Resolved | What 'working .twb' means with data locked in the model. | - | D7: header-only CSV stub with full field metadata; opens in Tableau. | Resolved
R7 | Risk | Filters are in the IR but not yet emitted as Tableau filters. | Medium | Next increment: map Condition trees to <filter class=categorical¦quantitative>. | Open - future work
R8 | Risk | Only 4 of 15 Regional measures translate. | Medium | By design (D5). Extending the subset needs CALCULATE semantics -> LOD expressions. | Open - future work